## Contents Page
These statements are the primary sources of information about Highways England’s performance in accordance with the ORR Monitoring Guidelines1
Notes
- Detailed information regarding efficiency delivery and statement in relation to inflationary impact will be contained in the published Highways England Efficiency Report
- Regional data for 2020-21 has been published on the Highways England website.
Contents
Performance Specification statements
PS1 | Improving safety for all
PS2 | Providing fast and reliable journeys
PS3 | A well maintained and resilient network
PS4 | Delivering better environmental outcomes
PS5 | Meeting the needs of all road users
PS6 | Achieving efficient delivery
Investment Plan statements
IP1 | Detailed analysis of enhancement monitoring milestones dates and lane miles delivered
IP2 | RIS 3 Development Pipeline
IP3 | Designated Funds
IP4 | Renewal Volume Reporting
IP5 | Maintenance Delivery Reporting
Financial Performance statements
F1 | Total income and expenditure
F2 | Regional resource income and expenditure
F2.1 | Resource income and projects expenditure
F2.2 | Analysis of protocols expenditure
F3 | Capital expenditure
F3.1 | Enhancement expenditure
F3.2 | Regional capital income and expenditure
Annual Statement
This report and its contents are taken as the Board’s statement of compliance with Highways England’s Licence and Framework Document obligations. It also confirms that Highways England maintains an effective assurance regime for the expenditure of public money and that its decision making meets the criteria set out in the Highways England Framework Document. This report constitutes Highways England’s annual progress report under clause 6.26 of the Licence. To the best of the Board’s knowledge and belief, having made all reasonable enquiries, the information contained in this document and the accompanying performance monitoring statements is set out appropriately. The Directors’ report was approved by the Board on 30 June 2021 and is signed on their behalf by: Nick Harris, CEO
1 https://www.orr.gov.uk/sites/default/files/om/monitoring-reporting-guidelines-for-highways-england-for-road-period-2.pdf

## PS1-Improving safety for all
Highways England Performance Monitoring Statements Year end 2020-21
Statement PS1: Improving safety for all |  |  | For a definition of the metric and parameters for measuring and monitoring safety performance see Highways England’s Operational Metrics Manual
Performance specification
| Source of Target | Actual | Target | KPI/PI | Difference (Actual vs Target) | Notes
KPI
The number of people killed or seriously injured on the SRN.
Ongoing reduction in the number of people killed or seriously injured on the SRN as reported in STATS19 to support a decrease of at least 50% by the end of 2025 against the 2005-09 average baseline. A +/- variance of 5% each year has been agreed with DfT Road User Safety Division to support this target.
Note: baseline will change each year as adjusted figures are produced
2005-09 baseline | Performance Specification | 2,321 (original)
3,094 (revised)
2015 | Unadjusted | 1,784 (original) | 1,750 (original) | KPI | 34 (original)
| Adjusted | 2,301 (revised) | 2,332 (revised) |  | -31 (revised)
2016 | Unadjusted | 2,005 (original) | 1,678 (original) | KPI | 327 (original)
| Adjusted | 2,223 (revised) | 2,237 (revised) |  | 83 (revised)
2017 | Unadjusted | 1,853 (original) | 1,607 (original) | KPI | 246 (original)
| Adjusted | 2,035 (revised) | 2,142 (revised) |  | -44 (revised)
2018 | Unadjusted | 1,987 (original) | 1,536 (original) | KPI | 451 (original)
| Adjusted | 2,152 (revised) | 2,047 (revised) |  | 187 (revised)
2019 | Unadjusted | 1,948 (original) | 1,464 (original) | KPI | 484 (original)
| Adjusted | 2,189 (revised) | 2,096 (revised) |  | 93 (revised)
2020 | Adjusted |  |  | KPI | 0
2021 | Adjusted |  |  | KPI | 0
2022 | Adjusted |  |  | KPI | 0
2023 | Adjusted |  |  | KPI | 0
2024 | Adjusted |  |  | KPI | 0
2025 | Adjusted |  |  | KPI | 0
In 2019 KSI casualties have decreased by 4.9% from 2015. Validated data for 2020 is expected at the end of September 2021. Changes in how police forces record road casualty data mean that it has not been possible to monitor progress against the target on a consistent basis during RIS1. To address this discontinuity, the DfT commissioned the Office for National Statistics to produce a robust methodology for adjusting historic road casualty data. This work concluded in 2018, and has enabled the Department to publish revised road casualty statistics that consistently account for the impact of CRASH over time.
PIs
The total number of people killed or injured on the SRN.
Illustrate the impact of activities undertaken by the company, and the influence of external factors with regards to making the network safer.
2015 | Performance Specification | 16375 | N/A | PI | N/A
2016 | Performance Specification | 16233 | N/A | PI | N/A
2017 | Performance Specification | 14225 | N/A | PI | N/A
2018 | Performance Specification | 13380 | N/A | PI | N/A |  | 7988 | 8387 | 16375
2019 | Performance Specification | 12347 | N/A | PI | N/A |  | 7792 | 8441 | 16233
2020 | Performance Specification |  | N/A | PI | N/A |  | 6930 | 7295 | 14225
2021 | Performance Specification |  | N/A | PI | N/A |  | 6507 | 6873 | 13380
2022 | Performance Specification |  | N/A | PI | N/A |  | 1948 | 10399 | 12347
2023 | Performance Specification |  | N/A | PI | N/A
2024 | Performance Specification |  | N/A | PI | N/A
2025 | Performance Specification |  | N/A | PI | N/A
Validated data for 2019 shows a 7.7% reduction year on year and a reduction of 24.6% from 2015.
The number of non-motorised and motorcyclist users killed or injured on the SRN.
The total number of pedestrian, pedal cyclist, motorcyclist and equestrian casualties on the SRN. Disaggregation will be provided by road user group to assist understanding of the PI but are not considered PIs in their own right.
2015 | Performance Specification | 1160 | N/A | PI | N/A
2016 | Performance Specification | 1170 | N/A | PI | N/A
2017 | Performance Specification | 1050 | N/A | PI | N/A
2018 | Performance Specification | 1036 | N/A | PI | N/A
2019 | Performance Specification | 962 | N/A | PI | N/A
2020 | Performance Specification |  | N/A | PI | N/A
2021 | Performance Specification |  | N/A | PI | N/A
2022 | Performance Specification |  | N/A | PI | N/A
2023 | Performance Specification |  | N/A | PI | N/A
2024 | Performance Specification |  | N/A | PI | N/A
2025 | Performance Specification |  | N/A | PI | N/A
Validated data for 2019 shows a 7.1% reduction year on year and a reduction of 17.1% from 2015.
The number of motorcyclist users killed or injured on the SRN.
2015 | Performance Specification | 849 | N/A | N/A | N/A
2016 | Performance Specification | 864 | N/A | N/A | N/A
2017 | Performance Specification | 760 | N/A | N/A | N/A
2018 | Performance Specification | 785 | N/A | N/A | N/A
2019 | Performance Specification | 694 | N/A | N/A | N/A
2020 | Performance Specification |  | N/A | N/A | N/A
2021 | Performance Specification |  | N/A | N/A | N/A
2022 | Performance Specification |  | N/A | N/A | N/A
2023 | Performance Specification |  | N/A | N/A | N/A
2024 | Performance Specification |  | N/A | N/A | N/A
2025 | Performance Specification |  | N/A | N/A | N/A
Validated data for 2019 shows a year-on-year decrease in motorcyclist casualties on the SRN.
The number of cyclists killed or injured on the SRN.
2015 | Performance Specification | 153 | N/A | N/A | N/A
2016 | Performance Specification | 152 | N/A | N/A | N/A
2017 | Performance Specification | 137 | N/A | N/A | N/A
2018 | Performance Specification | 103 | N/A | N/A | N/A
2019 | Performance Specification | 112 | N/A | N/A | N/A
2020 | Performance Specification |  | N/A | N/A | N/A
2021 | Performance Specification |  | N/A | N/A | N/A
2022 | Performance Specification |  | N/A | N/A | N/A
2023 | Performance Specification |  | N/A | N/A | N/A
2024 | Performance Specification |  | N/A | N/A | N/A
2025 | Performance Specification |  | N/A | N/A | N/A
Validated data for 2019 shows an increase in cyclist casualties on the SRN from 2018.
The number of pedestrians killed or injured on the SRN.
2015 | Performance Specification | 158 | N/A | N/A | N/A
2016 | Performance Specification | 154 | N/A | N/A | N/A
2017 | Performance Specification | 153 | N/A | N/A | N/A
2018 | Performance Specification | 148 | N/A | N/A | N/A
2019 | Performance Specification | 156 | N/A | N/A | N/A
2020 | Performance Specification |  | N/A | N/A | N/A
2021 | Performance Specification |  | N/A | N/A | N/A
2022 | Performance Specification |  | N/A | N/A | N/A
2023 | Performance Specification |  | N/A | N/A | N/A
2024 | Performance Specification |  | N/A | N/A | N/A
2025 | Performance Specification |  | N/A | N/A | N/A
Validated data for 2019 shows an increase in pedestrian casualties on the SRN from 2018.
The number of equestrians killed or injured on the SRN.
2015 | Performance Specification | 0 | N/A | N/A | N/A
2016 | Performance Specification | 0 | N/A | N/A | N/A
2017 | Performance Specification | 0 | N/A | N/A | N/A
2018 | Performance Specification | 0 | N/A | N/A | N/A
2019 | Performance Specification | 0 | N/A | N/A | N/A
2020 | Performance Specification |  | N/A | N/A | N/A
2021 | Performance Specification |  | N/A | N/A | N/A
2022 | Performance Specification |  | N/A | N/A | N/A
2023 | Performance Specification |  | N/A | N/A | N/A
2024 | Performance Specification |  | N/A | N/A | N/A
2025 | Performance Specification |  | N/A | N/A | N/A
Validated data for 2019 shows no equestrian casualties on the SRN.
Number of injury collisions on the SRN
The total number of collisions recorded that resulted in at least one injury (of any severity) on the SRN.
2020 | Performance Specification |  | N/A | PI | N/A
2021 | Performance Specification |  | N/A | PI | N/A
2022 | Performance Specification |  | N/A | PI | N/A
2023 | Performance Specification |  | N/A | PI | N/A
2024 | Performance Specification |  | N/A | PI | N/A
2025 | Performance Specification |  | N/A | PI | N/A
Validated data for 2020 is expected to be available in September 2021.
The accident frequency rate for Highways England staff
The accident frequency rate for Highways England staff based on Reporting of Injuries, Diseases and Dangerous Occurrences Regulations (RIDDOR) incidents and normalised by the number of hours worked in a year.
2020-21 | Performance Specification | 0.05 | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
The Highways England Accident Frequency Rate for 2020-21 is 0.05. Our Home Safe and Well approach sets out our vision and aspirations for safety, health and wellbeing, and how this will be achieved.
The accident frequency rate for Highways England supply chain staff
The accident frequency rate for Highways England supply chain staff based on Reporting of Injuries Diseases and Dangerous Occurrences Regulations (RIDDOR) incidents and normalised by the number of hours worked in a year.
2020-21 | Performance Specification | 0.05 | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
The supply chain Accident Frequency Rate for 2020-21 is 0.05. Alongside meeting with individual suppliers to review performance and action plans, regular safety leadership group meetings are being held with representation from across the supply chain to share best practise and common intent.
The % of traffic using iRAP 3* or above rated roads
IRAP based road safety investigations, developed in conjunction with the department, to feed into subsequent route strategies. Illustrate the impact of activities undertaken by the company, and the influence of external factors with regards to making the network safer. We are committed to ensure that 90% of travel on our roads is 3* rated or higher by 2020. The latest data indicates that 95% of travel on our roads is on 3-star rated roads or above which exceeds the target set in our delivery plan The percentage of travel on roads with an International Road Assessment Programme (iRAP) safety rating of 3-star or better calculated using the latest version of the iRAP model (version 3.02).
2020-21 | Performance Specification | N/A | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
A baseline star rating for our network is in development and is expected to be available for reporting later in 2021.
Commitments
Work with Transport Focus to investigate a rate-based measure for non-motorised user casualties. |  | The Pre-Concept and Concept milestones were met as planned in 2020-21. Following discussions with DfT, ORR and Transport Focus in December, it was then agreed to not progress further development of the metric due to the challenges in developing a reliable understanding of non-motorised users. Formal approval from DfT is now required to close this commitment.
1.1 Working with TF, investigate a rate-based measure for non-motorised user casualties
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | Following discussions with DfT, ORR and Transport Focus in December, it was then agreed to not progress further development.
Feasibility Stage | Q2 2021-22 | N/A
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
iRAP baseline to be established in 2021, and 2025 forecast developed, based on latest iRAP methodology. |  | This metric has been in operation but is being updated for RIS2 (v3.02) using a different version of the model used in RIS1 (v1.0). This will provide a baseline star rating assessment for our current 2020 network and provide a 2025 forecast which takes into account our current planned major investment programmes. Work is on track to meet the Development Stage milestone.
1.2 iRAP baseline to be established in 2021, and 2025 forecast and development, based on latest IRAP methodology
OMM Stages | Milestone
Concept Stage | N/A | N/A
Feasibility Stage | N/A | N/A
Development Stage | Q2 2021-22 | N/A
Validation Stage | N/A | N/A
Notes and commentary

## PS2-Fast and reliable
Highways England Performance Monitoring Statements Year end 2020-21
Statement PS2: Providing fast and reliable journeys |  | For a definition of the metric and parameters for measuring and monitoring User satisfaction see Highways England’s Operational Metrics Manual
Performance specification
| Source of Target | Actual | Target | KPI/PI | Difference (Actual vs Target) | Notes
KPI
Average Delay
Average delay to road users calculated as the difference between the observed travel time and the speed limit travel time.
Ambition – Performance to be no worse at the end of Road Period 2 than it is at the end of Road Period 1. Highways England will be required to demonstrate how it has acted to reduce delays in support of this ambition. This KPI does not have a target.
2020-21 | Performance Specification | 6.7 | Ambition | KPI
2021-22 | Performance Specification |  | Ambition | KPI
2022-23 | Performance Specification |  | Ambition | KPI
2023-24 | Performance Specification |  | Ambition | KPI
2024-25 | Performance Specification |  | Ambition | KPI
This is an amended metric for RIS2. It measures the delay experienced by individual vehicles based on the difference between the observed average travel time, and the speed limit travel time. The metric has observed reduced traffic flow due to Covid-19. In 2020-21 the average delay was 6.7 secs.
Network availability
The percentage of the strategic road network that is free from lane closures due to roadworks.
Target: Achieve 97.5% lane availability in 2020-21. The existing metric is expected to be replaced during 2020-21 by a new expanded metric. A baseline level of performance for the new metric will be determined in 2020-21 and will be used to set a target covering the remainder of Road Period 2.
2020-21 | Performance Specification | 98% | 97.5% | KPI | 0.5%
2021-22 | - |  |  | KPI | 0%
2022-23 | - |  |  | KPI | 0%
2023-24 | - |  |  | KPI | 0%
2024-25 | - |  |  | KPI | 0%
This metric is unchanged from RIS1. During 2020-21 we achieved a score of 98.0% of the network available to road users. Highways England successfully maintained performance above the 97.5% target throughout first year of RIS2. We are continuing to increase the volume and proportion of roadworks carried out at night, where there are lower traffic volumes to reduce the impact on our customers. We have worked closely with those companies for whom it is essential to use our network at night, such as parcel delivery firms, to mitigate the impact on them.
Incident clearance rate
The percentage of incidents on the motorway that impact traffic flow but are cleared in less than one hour.
Target: 86% of motorway incidents cleared within one hour.
2020-21 | Performance Specification | 88.6% | 86% | KPI | 2.6%
2021-22 | Performance Specification |  | 86% | KPI | -86%
2022-23 | Performance Specification |  | 86% | KPI | -86%
2023-24 | Performance Specification |  | 86% | KPI | -86%
2024-25 | Performance Specification |  | 86% | KPI | -86%
This is an amended metric for RIS2, including incidents across 24 hours rather than only those between 06:00 and 22:00hrs. Highways England successfully maintained the rolling year performance above the 86% target throughout first year of RIS2, achieving a clearance rate of 88.6%.
PIs
Delay on smart motorways
Average delay to road users on smart motorways calculated by comparing actual journey time with the minimum journey time (based on all vehicles travelling at upper limit for variable speed limit sections). It is a subset of the Average delay metric.
2020-21 | Performance Specification | 5.8 | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
This is a new metric for RIS2. It measures the delay experienced by individual vehicles based on the difference between the observed average travel time, and the speed limit travel time. The metric has observed reduced traffic flow due to Covid-19. In 2020-21 the delay on smart motorways was 5.8 secs.
Delay from roadworks
This metric measures the additional journey time during roadworks for all vehicle types, compared to an average benchmark journey time measured before the roadworks were in place. Calculated as average annual delay (minutes per hour travelled).
2020-21 | Performance Specification | 0.94 | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
This is a new metric for RIS2. It measures the total additional delay during roadworks, compared to an average benchmark journey time measured before the roadworks were in place. The metric has observed reduced traffic flow due to Covid-19. In 2020-21 the delay during roadworks was 0.94 mins per hour.
Journey time reliability
The average difference between the observed travel time and the profile (typical) travel time.
2020-21 | Performance Specification | 1.9 | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
This is a new metric for RIS2. It measures the average delay above the typical profile delay that occurs on the Strategic Road Network. The metric has observed reduced traffic flow due to Covid-19. In 2020-21 the journey time reliability was 1.9 seconds per vehicle per mile.
Delay on gateway routes
Average delay to users of gateway routes. Delay is calculated by comparing actual journey time with the minimum journey time (based on all vehicles travelling at the speed limit). It is a subset of the average delay metric.
2020-21 | Performance Specification | 5.6 | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
This is an amended metric for RIS2. It measures the delay experienced by individual vehicles based on the difference between the observed average travel time, and the speed limit travel time. The metric has observed reduced traffic flow due to Covid-19. In 2020-21 the delay on gateway routes was 5.6 seconds per vehicle per mile.
Average speed
The average speed of vehicles travelling on the strategic road network
2020-21 | Performance Specification | 60.7 | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
This is an amended metric for RIS2. It measures the average speed of vehicles travelling on the Strategic Road Network (SRN) which is the total miles travelled divided by the total hours spent travelling. The metric has observed reduced traffic flow due to Covid-19. The average speed across the SRN for 2020-21 was 60.7 miles per hour.
Commitments
Network availability KPI: Existing metric to be replaced by a new expanded metric with target based on baseline work undertaken during 2020-21 |  | Highways England successfully developed enhanced (Roadworks Network Impact) metric in line with our expected milestones for 2020-21.
2.1 Network availability KPI: Existing metric to be replaced by a new expanded metric with target based on baseline work undertaken during 2020-21
OMM Stages | Milestone
Concept Stage | - | N/A
Feasibility Stage | - | N/A
Development Stage | Q3 2020-21 | The milestone was achieved in Q3 2020-21.
Validation Stage | Q4 2020-21 | The milestone was achieved in Q4 2020-21.
Working with Transport Focus, investigate the development of new metrics on journey time reliability which reflects more accurately road users’ understanding of reliability, and delay in roadworks. |  | Highways England successfully completed the Concept stage in developing the new metrics on journey time reliability and delay in roadworks in line with our expected milestones for 2020-21. Work is on track to complete the Feasibility stage of these metrics in development in Q2 2021-22.
2.2 Working with TF, investigate the development of the new metrics on journey time reliability which reflects more accurately road users understanding of reliability, and delay in roadworks
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | The milestone was achieved in Q3 2020-21.
Feasibility Stage | Q2 2021-22 | N/A
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
Investigate new PIs on delays from incidents and delays on the local road/SRN boundary, and an alternative performance measure for smart motorway operation to keep track that these roads are delivering their intended journey-time related objectives. |  | Highways England successfully completed the Concept stage for all 3 metrics in development in line with our expected milestones for 2020-21. However, following the Concept stage investigation, it was established that the desired outcomes of the new metric for delays on the local road and Strategic Road Network (SRN) boundary can be achieved using existing metrics. Engagement with the DfT, ORR and Transport Focus is taking place to discuss ceasing further development of the metric. Work is on track to complete the Feasibility stage of delay from incidents and alternative performance measure for smart motorways operation metrics in development in Q2 2021-22.
2.3 Investigate new PIs on delays from incidents &delays on local road/ SRN boundary, & an alternative perf. Measure for smart motorway operation to keep track that these roads are delivering their intended journey-time related objectives
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | The milestone was achieved in Q3 2020-21.
Feasibility Stage | Q2 2021-22 | N/A
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
Notes and commentary

## PS3-Maintainance and resilience
Highways England Performance Monitoring Statements Year end 2020-21
Statement PS3: A well maintained and resilient network |  | For a definition of the metric and parameters for measuring and monitoring the flow of traffic see Highways England’s Operational Metrics Manual
Performance specification
| Source of Target | Actual | Target | KPI/PI | Difference (Actual vs Target) | Notes
KPIs
Pavement condition
The percentage of pavement asset that does not require further investigation for possible maintenance. This measure reports on the overall strategic road network condition as a result of deterioration of the pavement network due to time and traffic and restoration of condition from the annual investment in maintenance. Target: Percentage of the network (as defined by HAPMS, excluding DBFOs) requiring no further investigation to be maintained at 95% or above.
2020-21 | Performance Specification | 95.2% | 95% | KPI | 0.2%
2021-22 | Performance Specification |  | 95% | KPI | -95%
2022-23 | - |  |  | KPI | 0%
2023-24 | - |  |  | KPI | 0%
2024-25 | - |  |  | KPI | 0%
The pavement condition indicator has been consistently delivering to the target of 95% since 2018-19, ending the 2020-21 year with 95.2%. The metric is the same as RIS1 until 2022 when the new indicator is finalised.
PIs
Structures condition
The condition of Highways England’s structures across the strategic road network.
2020-21 | Performance Specification | 81.2% | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
All three elements of the structures metric have seen improvement across this road period, with average condition delivering 85.42%, critical condition 63.33% and structures rated as good 81.2% respectively. This indicator has no target.
Technology availability
The percentage of time that roadside technology assets are available and functioning. The assets are considered available and functioning if they are not experiencing a service-affecting fault.
2020-21 | Performance Specification | 95.06% | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
This is a new metric for this road period. The metric now is focused on overall availability and has averaged 96% throughout the year to date. This indicator has no target.
Drainage resilience
The percentage length of carriageway that does not have an observed significant susceptibility to flooding
2020-21 | Performance Specification | 72% | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
This is a new metric for this road period. The new drainage condition indictor reports carriageway (catchment length) that does not have an observed significant susceptibility to flooding. Delivering consistently above 70%, the March 2021 reported figure of was 72%; this does not mean that 28% of the network is at high risk of flooding, but that 28% of network has catchments that include high risk flood hotspots.
Geotechnical condition
The percentage length of the Highways England’s geotechnical asset that is in good condition based on the ability of the asset to perform its function at the time of inspection (i.e. to support other highways assets).
2020-21 | Performance Specification | 99.62% | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
This is a new metric for this road period. The geotechnical asset condition performance for March 2021 is reported as 99.62% of the asset length in the good condition category based on a condition grade. The condition grade considers the ability of the geotechnical asset to perform its function at the time of inspection.
Commitments
Implement the AMDP for RP2 as described above. |  | Highways England has progressed the development of its asset management capability through the Asset Management Transformation Programme (AMTP) which was established in April 2020 to deliver the Asset Management Development Plan (AMDP) commitment. Progress has been made in this first year of the road period against a number of milestones in the AMDP.
3.1 Implement the AMDP for RP2 as described above (in the RIS document)
OMM Stages / milestone
Agree AMDP deliverables for the following financial year: Q4 each year |  | The milestone was achieved in Q4 2020-21.
End of year report: Q1 the following year |  | N/A
End of year review of deliverables: Q2 the following year |  | N/A
Investigate an improved structure condition metric during RP2, and an alternative indicator for technology assets |  | Highways England successfully met the Concept Stage milestone in 2020-21 and is on target to deliver against the Feasibility stage by Q2 2021-22. Engagement with the DfT, ORR and Transport Focus has taken place and feedback fed into Feasibility.
3.2 Investigate an improved structure condition metric during RP2, and an alternative indicator for technology assets
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | The milestone was achieved in Q3 2020-21 for both Structure and Technology.
Feasibility Stage | Q2 2021-22 | N/A
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
Pavement condition KPI: Target for 3 years onward will be based on the concept of road surface in good condition and determined through parallel running using the new metric trialled in RP1 |  | No milestones for 2020-21. On target for Validation Stage milestone Q4 2021-22.
3.3 Pavement condition KPI: Target for 3 years onward will be based on the concept of road surface in good condition and determined through parallel running using the new metric trialled in RP1
OMM Stages | Milestone
Concept Stage | - | N/A
Feasibility Stage | - | N/A
Development Stage | - | N/A
Validation Stage | Q4 2021-22 | N/A
Drainage condition PI: From 2024/25 it is intended that this metric will be weather normalised |  | No milestones for 2020-21. On target for Development Stage milestone Q3 2021-22.
3.4 Drainage condition PI: From 2024/25 it is intended that this metric will be weather normalised
OMM Stages | Milestone
Concept Stage | - | N/A
Feasibility Stage | - | N/A
Development Stage | Q4 2021-22 | N/A
Validation Stage | Q3 2023-24 | N/A
Notes and commentary

## PS4 - Environment
Highways England Performance Monitoring Statements Year end 2020-21
Statement PS4 Delivering better environmental outcomes |  | For a definition of the metric and parameters for measuring and monitoring the flow of traffic see Highways England’s Operational Metrics Manual
Performance specification
| Source of Target | Actual | Cumulative | Target | KPI/PI | Difference (Actual vs Target) |  | Notes
KPIs
Noise
The number of households within mitigated Noise Important Areas where noise has been reduced through Highways England designated fund projects.
Target: 7,500 households benefitting from noise reduction in mitigated Noise Important Areas (defined by the Department for Environment, Food and Rural Affairs (DEFRA)) using funding from the environment and wellbeing designated fund during Road Period 2 | [6 empty] | This is an amended metric for RIS2. In 2020-21 we reduced noise levels for 2111 households within Noise Important Areas. We also benefitted a further 710 households as part of our business as usual activities which do not count towards the KPI.
2020-21 | Performance Specification | 2111 | 2111 | 7500 | KPI | -5389
2021-22 | Performance Specification |  |  | 7500 | KPI | -7500
2022-23 | Performance Specification |  |  | 7500 | KPI | -7500
2023-24 | Performance Specification |  |  | 7500 | KPI | -7500
2024-25 | Performance Specification |  |  | 7500 | KPI | -7500
Biodiversity
Deliver no net loss of biodiversity, measured using an industry standard way of measuring biodiversity changes referred to as the biodiversity metric.
Target: Achieve no net loss of biodiversity, across all Highways England activities, by the end of Road Period 2.
2020-21 | - | 115.4 | N/A | No net loss | KPI
2021-22 | - |  | N/A | No net loss | KPI
2022-23 | - |  | N/A | No net loss | KPI
2023-24 | - |  | N/A | No net loss | KPI
2024-25 | - |  | N/A | No net loss | KPI
This is a new metric for RIS2. We delivered 115.4 biodiversity units (BU) in 2020-21 and the biodiversity baseline was validated as 130,848.1. At end of year 1 we have identified a forward programme which will deliver c.3,572BU that contribute towards achieving KPI.
Air Quality
The number of strategic road network links in exceedance of the legal nitrogen dioxide (NO2) limits as set by the European Union and accepted by the government.
Bring links agreed with the department and based on the Pollution Climate Mapping model into compliance with legal NO2 limits in the shortest timescales possible
This is a new metric for RIS2. At end of 2020-21 the total number of Pollution Climate Mapping (PCM) links in exceedance is 31. We continued working on identifying mitigations for those links where this is possible. For those links where studies have concluded that no viable measures exist we have written to DfT setting out our position. During 2020-21 we also invested AQ Designated Funding into six electric van centres of excellence. These schemes are anticipated to accelerate the update of low emission vehicles on several non-compliant links.
Highways England carbon emissions
Target: Reduce Highways England’s carbon emissions as a result of electricity consumption, fuel use and other day-to-day operational activities during RP2, to levels defined by baselining and target setting activities in 2020-21. This metric will become operational from 1 April 2021.
2020-21 | - |  | N/A |  | KPI | 0
2021-22 | - |  | N/A |  | KPI | 0
2022-23 | - |  | N/A |  | KPI | 0
2023-24 | - |  | N/A |  | KPI | 0
2024-25 | - |  | N/A |  | KPI | 0
This will be a new metric for RIS2. The Highways England Carbon metric will start reporting from April 2021. The target is to reduce carbon emissions by 75% across the RIS2 period, based on emissions from April 2017 to March 2018. This will see a reduction from 88,147 tonnes to 22,037 tonnes. This baseline and target has been successfully developed over year 1 of RIS2.
PIs
Supply Chain Carbon emissions
The carbon footprint associated with Highways England’s supply chain and also normalised by the volume of work undertaken.
|  | Absolute | Normalised
2020-21 | Performance Specification | 365353 | - | N/A | PI | N/A
2021-22 | Performance Specification |  |  | N/A | PI | N/A
2022-23 | Performance Specification |  |  | N/A | PI | N/A
2023-24 | Performance Specification |  |  | N/A | PI | N/A
2024-25 | Performance Specification |  |  | N/A | PI | N/A
This is an ongoing metric from RIS1. The validated position is 365,353.00 tonnes/CO2e for 2020-21. Highways England is engaging and focusing support for the supply chain to further improve reporting on carbon emissions.
Condition of Cultural Heritage assets
The overall condition of the culturally significant assets owned by Highways England.
2020-21 | Performance Specification | 51556 | N/A | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | N/A | PI | N/A
This is a new metric for RIS2. We established our cultural heritage baseline at 51,556 units over the course of 2020-21. We also completed improvement works which increased the baseline by 12 units during the same period.
Water Quality
The length of watercourse enhanced through the mitigation of medium, high, and very high risk outfalls as well as through other enhancements, for example river retraining/rewilding.
2020-21 | Performance Specification | 17 | N/A | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | N/A | PI | N/A
This is an altered metric for RIS2. We delivered 23 outfalls, 1 fish pass and 1 natural flood management scheme in 2020-21. This resulted in 16.681 km of watercourse enhanced.
Litter
The percentage of the strategic road network where litter is graded at A or B as defined in the Code of practice on litter and refuse 2006.
2020-21 | Performance Specification | 49.2% | N/A | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | N/A | PI | N/A
This is a new metric for RIS2. It measures the percentage of the Strategic Road Network where litter is graded at A or B as defined in the Code of practice on litter and refuse. The metric covers the whole of the Asset Delivery network on an annual basis, and was reported for the first time in 2020-21. The reported performance for 2020-21 was 49.2%
Commitments
Highways England carbon emissions KPI: Reduce Highway England's carbon emissions as a direct result of electricity and fuel use & the day to day operational activities during RP2, to levels defined by baselining & target setting activities in 2020-21 |  |  |  |  | This will be a new metric for RIS2. The commitment to baseline and set a target for this metric was met in 2020-21. The metric will be operational from April 2021.
4.1 Highways England carbon emissions KPI: Reduce Highway England's carbon emissions as a direct result of electricity and fuel use & the day to day operational activities during RP2, to levels defined by baselining & target setting activities in 2020-21
OMM Stages | Milestone
Inventory and asset register update; data collation including project action plans | Q3 2020-21 | The milestone was achieved in Q3 2020-21.
Start of formal sign-off process of new metric and target with DfT | Q4 2020-21 | The milestone was achieved in Q4 2020-21.
Completion of validation; approvals of target | Q4 2020-21 | The milestone was achieved in Q4 2020-21.
Validation Stage | Q4 2020-21 | The milestone was achieved in Q4 2020-21.
Investigate, and as appropriate develop, new environmental metric(s) informed by the natural capital approach. |  |  |  |  | The Concept Stage milestone was achieved in Q4 2020-21 due to the need for extended engagement with external stakeholders.
4.2 Investigate, and as appropriate develop, new environmental metric(s) informed by the natural capital approach
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | The milestone was achieved in Q4 2020-21 due to the need for extended engagement with external stakeholders.
Feasibility Stage | Q2 2021-22 | N/A
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
Investigate and assess incorporating into new and existing contracts air quality standards for supply chain vehicles deployed on Highways England work, and associated reporting requirements. A more detailed timetable for these investigations will be produced in Year 1 of RP2, as well as potential implementation opportunities identified by that stage. |  |  |  |  | The Concept Stage was achieved in Q4 2020-21. A detailed timetable was produced in 2020-21 in line with the commitment.
4.3 Investigate and assess incorporating into new and existing contracts air quality standards for supply chain vehicles deployed on highways England work, and associated reporting requirements. A more detailed timetable for these investigations will be produced in year 1 od RP2, as well as potential implementation opportunities identified by that stage.
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | The milestone was achieved in Q4 2020-21. A detailed timetable was produced in 2020-21 in line with the commitment.
Feasibility Stage | Q2 2021-22 | N/A
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
Notes and commentary

## PS5-Needs of all road users
Highways England Performance Monitoring Statements Year end 2020-21
Statement PS5: Meeting the needs of all road users |  |  |  | For a definition of the metric and parameters for measuring and monitoring performance regarding vulnerable users see Highways England’s Operational Metrics Manual
Performance specification
| Source of Target | Actual | Target | KPI/PI | Difference (Actual vs Target) | Notes
KPIs
Road user satisfaction
The percentage of drivers who are satisfied with their journey on the strategic road network as measured by the Strategic Roads User Survey (SRUS) conducted by Transport Focus.
Target: Achieve an 82% road user satisfaction score in 2020-21 and 2021-22, with year-on-year increases in the following years. The exact targets for 2022-23, 2023-24, and 2024-25 will be set during 2021-22.
2020-21 | Performance Specification | N/A | 82% | KPI | N/A
2021-22 | Performance Specification |  | 82% | KPI
2022-23 |  |  |  | KPI
2023-24 |  |  |  | KPI
2024-25 |  |  |  | KPI
This is a new metric for RIS2. The Strategic Roads User Survey (SRUS) has not been carried out by Transport Focus this financial year, and it has not been possible to monitor progress for the KPI. This is due to Covid-19 and social distancing measures preventing a face to face survey. A web-based alternative survey, Push-to-Web, has been trialled over 2020-21, and will be run over 2021-22, however the methodology and demographics are different, and it is not formally a direct replacement for the existing SRUS at this time.
Roadworks information timeliness and accuracy
The percentage of overnight road closures that are accurately notified by Highways England seven days in advance. A correctly notified road closure is one that commences within +/- 1 hour of the start time stated 7 days in advance on the Network Occupancy Management System (NOMS).
Target: Achieve 90% accuracy of roadworks information seven days (rolling) in advance of works by 2024-25, with an increasing trajectory of improvement through Road Period 2 from the level of performance achieved by the end of Road Period 1
2020-21 | Performance Specification | 54.5% |  | KPI
2021-22 | Performance Specification |  |  | KPI
2022-23 | Performance Specification |  |  | KPI
2023-24 | Performance Specification |  |  | KPI
2024-25 | Performance Specification |  | 90% | KPI
This is a new metric for RIS2. The metric's performance has improved significantly over it's first 12 months. With more data now available, work continues to better understand the performance figures in order to continue driving improvements to reach targeted levels for April 2024 (this enables maintenance of performance for the rolling target for the end of the RIS).
PIs
Timeliness of information provided to road users through electronic signage
The average median time to set signs and signals on (all) motorways after Highways England has received notification of an incident, that requires signs and signals to be manually set.
2020-21 | Performance Specification | 0:02 | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
This is a new metric for RIS 2. It measures the average median time that it takes for Highways England to set signs and signals nationally. Throughout this financial year the performance has been consistent with the highest reported figure being 2m 02s in December 2020.
Ride Quality
This measure reports the ride quality for the strategic road network using a subset of the pavement condition metric condition parameters. It is represented by the percentage of pavement asset delivering ride quality consistent with the 3m Enhanced Longitudinal Profile Variance (ELPV) value in Highways England’s standards, which is based on engineering factors and driver comfort. Percentage of the network (as defined by HAPMS, excluding DBFOs) where 3m ELPV is deemed to be category 2 and better, in accordance with the road condition standard, HD29.
2020-21 | Performance Specification | 98.5% | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
This is a new metric for RIS2. Performance over 2020-21 has been stable for Ride Quality.
Working with local highways authorities to review diversion routes for unplanned events.
2020-21 | Performance Specification | 53% | N/A | PI | N/A
2021-22 | Performance Specification |  | N/A | PI | N/A
2022-23 | Performance Specification |  | N/A | PI | N/A
2023-24 | Performance Specification |  | N/A | PI | N/A
2024-25 | Performance Specification |  | N/A | PI | N/A
This is a new metric for RIS2. It reports on an annual basis, the percentage of local highway authorities which Highways England engaged with, to review diversion routes for unplanned events. The reported performance for 2020-21 was 53%.
Commitments
Work with Transport Focus to develop satisfaction surveys for cyclists and pedestrians that can be used, if possible, as the basis of a PI later in RP2. |  |  |  | There were no in-year milestones to meet in 2020-21. Highways England is engaged with Transport Focus in the development of the cyclist and pedestrian satisfaction survey, currently seeking a trial survey.
5.1 Work with TF to develop satisfaction surveys for cyclists & pedestrians that can be used, if possible, as the basis of a PI later in RP2
OMM Stages |  | Milestone
Concept Stage |  | Transport focus led commitment | N/A
Feasibility Stage |  | Transport focus led commitment | N/A
Development Stage |  | Transport focus led commitment | N/A
Validation Stage |  | Transport focus led commitment | N/A
Work with Transport Focus to develop satisfaction surveys for logistics and coach managers that can be used, if possible, as the basis of a PI later in RP2. |  |  |  | There were no in-year milestones to meet in 2020-21. Highways England are currently awaiting results from a Wave 2 survey being conducted by Transport Focus. If the analysis of results is clear and consistent, then benchmarking and an action plan moving forwards will be considered.
5.2 Work with TF to develop satisfaction surveys for logistics & coach managers that can be used, if possible, as the basis of a PI later in RP2
OMM Stages |  | Milestone
Concept Stage |  | Transport focus led commitment | N/A
Feasibility Stage |  | Transport focus led commitment | N/A
Development Stage |  | Transport focus led commitment | N/A
Validation Stage |  | Transport focus led commitment | N/A
Review SRUS performance in year 2 of RP2 to determine the road user satisfaction targets for post 2021-22. |  |  |  | There were no in-year milestones to meet in 2020-21. The SRUS (face to face) survey suspended due to Covid-19. Highways England have sought suspension of the target for 2020-21 and 2021-22. An alternative online survey (push-to-web) has been developed by Transport Focus, and initial findings shared, though the methodology and demographics are different from SRUS. Push-to-web is due to commence from April 2021.
5.3 Review SRUS performance in year 2 of RP2 to determine the road user satisfaction targets for post 2021-22
OMM Stages |  | Milestone
Concept Stage |  | N/A | N/A
Feasibility Stage |  | N/A | N/A
Development Stage |  | N/A | N/A
Validation Stage |  | Q4 2021-22 | N/A
Develop with Transport Focus during RP2 a measure of ride quality which reflects road users’ experience of the network. |  |  |  | Both the Concept Stage and Feasibility Stage milestones were met. We are currently in the Development Stage due for review in Q2 2021-22.
5.4 Develop with Transport Focus during RP2 a measure of ride quality which reflects road users' experience of the network
OMM Stages |  | Milestone
Concept Stage |  | Q2 2020-21 | The milestone was achieved in Q2 2020-21.
Feasibility Stage |  | Q4 2020-21 | The milestone was achieved in Q4 2020-21.
Development Stage |  | Q2 2021-22 | N/A
Validation Stage |  | Q4 2021-22 | N/A
Investigate expanding the scope of the working with local highways authorities PI to include diversion routes linked to planned roadworks. |  |  |  | The Concept Stage milestone was achieved in Q4 2020-21 due to the need for extended engagement with external stakeholders. We are currently in the Feasibility stage due for review in Q2 2021-22.
5.5 Investigate expanding the scope of the working with local highways authorities PI to include diversion routes linked to planned roadworks
OMM Stages |  | Milestone
Concept Stage |  | Q3 2020-21 | The milestone was achieved in Q4 2020-21 due to the need for extended engagement with external stakeholders.
Feasibility Stage |  | Q2 2021-22 | N/A
Development Stage |  | TBC following review | N/A
Validation Stage |  | TBC following review | N/A
Investigate expanding the scope of the timeliness of electronic signage information PI to potentially include the time taken to adjust and clear signs. |  |  |  | The Concept Stage is pending final approval due to ongoing engagement required. The investigation findings have suggested that there are limitations in collecting and calculating the data, therefore further conversations are taking place with DfT, ORR and Transport Focus on how to move forward.
5.6 Investigate expanding the scope of the timeliness of electronic signage information PI to potentially include the time taken to adjust and clear signs
OMM Stages |  | Milestone
Concept Stage |  | Q3 2020-21 | The Concept Stage is pending final approval due to ongoing engagement required.
Feasibility Stage |  | Q2 2021-22 | N/A
Development Stage |  | TBC following review | N/A
Validation Stage |  | TBC following review | N/A
Notes and commentary

## PS6-Efficiency of delivery
Highways England Performance Monitoring Statements Year end 2020-21
Statement PS6: Achieving efficient delivery
Performance specification
| Source of Target |  | Actual (£m) | Annual forecast milestone (£m) | KPI/PI | Difference (Actual vs Target) | Notes
KPIs
Total efficiency
The value of operational and capital expenditure efficiency achieved by the end of Road Period 2.
Target: Demonstrate efficiency of £2.230 bn of capital and operational expenditure by the end of Road Period 2. | [6 empty] | The annual forecast milestones numbers will be updated annually in line with Delivery Plan update.
2020-21 | EIMM | In-year: | 243 | 233 | KPI
|  | Cumulative: | 243 | 233 | KPI | 10
2021-22 | EIMM | In-year: |  | 238 | KPI
|  | Cumulative: | 243 | 471 | KPI | -228
2022-23 | EIMM | In-year: |  | 405 | KPI
|  | Cumulative: | 243 | 876 | KPI | -633
2023-24 | EIMM | In-year: |  | 508 | KPI
|  | Cumulative: | 243 | 1384 | KPI | -1141
2024-25 | Performance Specification | In-year: |  | 846 | KPI
|  | Cumulative: | 243 | 2230 | KPI | -1987
PIs
Cost performance index and Schedule performance index Progress of schemes in construction through reporting Cost performance index (CPI) and Schedule performance index (SPI).
25 Construction Phase projects reported Indices reported are Cumulative end of March 2020
Cost Performance Index (CPI): Represents the amount of work being completed on a project for every unit of cost spent. CPI is computed by Earned Value / Actual Cost . A value of above 1 means that the project is doing well against the budget. Schedule Performance Index (SPI): Represents how close actual work is being completed compared to the schedule. SPI is computed by Earned Value / Planned Value. A value of above one means that the project is doing well against the schedule. *Values generated manually through assessments by PMOs
Commitments
Investigate and look to develop new or improved metrics to monitor cost and schedule for enhancement scheme development and construction, engaging with ORR. |  |  |  |  | The metric is not ready to be considered / developed by Major Projects. Engagement with the metric owner to date suggests there is a focus on establishing CPI/SPI for schemes in construction to meet present commitments.
6.1 Investigate & look to develop new or improved metrics to monitor cost & schedule for enhancement scheme development & construction, engaging with ORR
OMM Stages | Milestone
Concept Stage | Q3 2020-21 | N/A
Feasibility Stage | Q2 2021-22 | N/A
Development Stage | TBC following review | N/A
Validation Stage | TBC following review | N/A
Notes and commentary

## IP1
Statement IP1: Detailed analysis of enhancement monitoring milestones dates and lane miles delivered
Highways England Delivery Plan - Major Improvements
Milestone Definitions and Key:
Construction Phase - Start of Works - The date when the start of the works is declared, following approval of final business case and construction budget, award of contract is in place along with completion of “Notice to proceed” and where applicable the “Notice to Treat”. Physical construction works will be evident on site.
Open for Traffic - The date when works are substantially complete and the scheme is open to traffic. There may be partial or overnight closures to finalise any remedial works.
Delivery Plan Commitment - The date committed to in Highways England's 2020-2025 delivery plan.
Actual Achieved - The actual date the Delivery Plan commitment has been achieved.
*Scheme commitment under review - Scheme is under review and is subject to formal change control governance.
| Region | Map Ref | Scheme Name | Construction Phase
|  |  |  | Start of Works (SOW) |  | Open for Traffic
|  |  |  | Delivery Plan Commitment | Actual Achieved | Delivery Plan Commitment | Actual Achieved | Lane miles delivered (Actual)
Highways England schemes | North East | 1 | A1 Scotswood to North Brunton | Pre RP2 | 2020-03-11 | 2022/2023
|  | 2 | A19 Testos | Pre RP2 | 2019-03-21 | 2021/2022 Q3
|  | 3 | A19 Norton to Wynyard | Pre RP2 | 2020-03-27 | 2022/2023
|  | 4 | M621 Junctions 1-7 | Pre RP2 | 2019-11-18 | 2022/2023
|  | 5 | A61 Westwood Roundabout | Pre RP2 | 2020-03-27 | 2021/2022 Q1 | 2021-02-28 | 0
|  | 6 | A1 Morpeth to Ellingham | 2022/2023 Q2 |  | 2024/2025
|  | 7 | A1 Birtley to Coal House | 2021/2022 Q2 |  | 2024/2025
|  | 8 | A19 Down Hill Lane | 2020/2021 Q4 | 2020-09-14 | 2022/2023
|  | 9 | A63 Castle Street | Pre RP2 | 2020-03-31 | 2024/2025
|  | 10 | M62 Junctions 25-30 | 2021/2022 Q4 |  | 2022/2023
| North West | 11 | A585 Windy Harbour to Skippool | Pre RP2 | 2020-03-27 | 2023/2024
|  | 12 | M62 Junctions 20-25 | 2022/2023 Q4 |  | RP3
|  | 13 | M6 Junction 19 | Pre RP2 | 2020-03-25 | 2021/2022 Q3
|  | 14 | A66 Northern Trans-Pennine | *2024/2025 | *Scheme commitment under review | -
|  | 15 | A5036 Princess Way | 2023/2024 |  | RP3
|  | 16 | M6 Junctions 21a-26 | 2020/2021 Q4 | 2021-03-22 | 2022/2023
|  | 17 | Mottram Moor Link Road & A57 Link Road | 2022/2023 Q4 |  | RP3
|  | 18 | M56 Junctions 6-8 | Pre RP2 | 2020-03-30 | 2021/2022 Q4
|  | 19 | M60/M62/M66 Simister Island Interchange | 2024/2025 |  | -
| Midlands | 20 | A500 Etruria | Pre RP2 | 2019-02-04 | 2020/2021 Q3 | 2020-07-03 | 1
|  | 21 | M6 Junctions 13-15 | Pre RP2 | 2018-03-20 | 2021/2022 Q2
|  | 22 | M42 Junction 6 | Pre RP2 | 2020-03-16 | 2024/2025
|  | 23 | A46 Coventry Junctions | Pre RP2 | 2020-03-25 | RP3
|  | 24 | M40/M42 Interchange | Pre RP2 | 2020-02-24 | 2023/2024
|  | 25 | A45/A6 Chowns Mill Junction | Pre RP2 | 2019-11-25 | 2021/2022 Q4
|  | 26 | M1 Junctions 13-19 | Pre RP2 | 2015-11-30 | 2022/2023
|  | 27 | A38 Derby Junctions | 2021/2022 Q2 |  | 2024/2025
|  | 28 | M54-M6 Link Road | 2021/2022 Q4 |  | 2024/2025
|  | 29 | A5 Dodwells to Longshoot | 2024/2025 |  | RP3
|  | 30 | A52 Nottingham Junctions | Pre RP2 | 2017-01-16 | 2023/2024
|  | 31 | M6 Junction 10 | Pre RP2 | 2020-01-31 | 2022/2023
|  | 32 | A46 Newark Bypass | 2024/2025 |  | -
|  | 33 | M42 Junctions 4-7 | 2023/2024 |  | 2024/2025
|  | 34 | M6 Junctions 4-5 | 2021/2022 Q2 |  | 2022/2023
|  | 35 | M6 Junctions 5-8 | 2022/2023 Q4 |  | 2024/2025
|  | 36 | M6 Junctions 8-10a | 2023/2024 |  | 2024/2025
| East | 37 | A14 Cambridge to Huntingdon | Pre RP2 | 2016-10-14 | 2020/2021 Q3 | 2020-05-05 | 134
|  | 38 | A47 Wansford to Sutton | 2022/2023 Q4 |  | 2024/2025
|  | 39 | A47 Great Yarmouth Junctions | 2023/2024 |  | 2024/2025
|  | 40 | A47 Guyhirn Junction | 2020/2021 Q4 | 2021-02-24 | 2022/2023
|  | 41 | A47 North Tuddenham to Easton | 2022/2023 Q4 |  | 2024/2025
|  | 42 | A47 Thickthorn Junction | 2022/2023 Q4 |  | 2024/2025
|  | 43 | A47 Blofield to North Burlingham | 2022/2023 Q4 |  | 2024/2025
|  | 44 | A428 Black Cat to Caxton Gibbet | 2022/2023 Q2 |  | RP3
|  | 45 | A12 Chelmsford to A120 | 2023/2024 |  | RP3
|  | 46 | M1 Junctions 10-13 | 2022/2023 Q2 |  | 2023/2024
| South East | 47 | M4 Junctions 3-12 | Pre RP2 | 2017-03-27 | 2021/2022 Q4
|  | 48 | A34 Newbury to Oxford Enhancements | Pre RP2 | 2019-08-12 | 2021/2022 Q4
|  | 49 | M3 Junctions 9-14 | Pre RP2 | 2020-01-13 | 2023/2024
|  | 50 | M27 Junctions 4-11 | Pre RP2 | 2018-04-03 | 2021/2022 Q2
|  | 51 | M25 Junction 25 | 2020/2021 Q4 | 2021-01-04 | 2022/2023
|  | 52 | M25 Junction 28 | 2021/2022 Q4 |  | 2024/2025
|  | 53 | M25 Junctions 10-16 | 2022/2023 Q2 |  | RP3
|  | 54 | M25 Junction 10 | 2021/2022 Q4 |  | 2023/2024
|  | 55 | M3 Junction 9 | 2023/2024 |  | RP3
|  | 56 | M27 Southampton Junction 8 | 2021/2022 Q2 |  | 2022/2023
|  | 57 | A27 Arundel Bypass | 2023/2024 |  | RP3
|  | 58 | A27 Worthing and Lancing improvements | 2024/2025 |  | RP3
|  | 59 | A31 Ringwood | 2021/2022 Q2 | 2021-03-31 | 2022/2023
|  | 60 | A2 Bean and Ebbsfleet | Pre RP2 | 2020-03-30 | 2022/2023
|  | 61 | M2 Junction 5 | *2020/2021 Q4 | *Scheme commitment under review | 2024/2025
|  | 62 | A27 East of Lewes Package | Pre RP2 | 2020-03-24 | 2022/2023
|  | 63 | Lower Thames Crossing | 2022/2023 Q4 |  | RP3
| South West | 64 | A303 Sparkford to Ilchester | *2020/2021 Q4 | *Scheme commitment under review | 2023/2024
|  | 65 | A303 Amesbury to Berwick Down | 2022/2023 Q2 |  | RP3
|  | 66 | A358 Taunton to Southfields | 2024/2025 |  | RP3
|  | 67 | A30 Chiverton to Carland Cross | Pre RP2 | 2020-03-31 | 2023/2024
|  | 68 | A417 Air Balloon | 2022/2023 Q4 |  | 2024/2025
|  | 69 | M4 Junctions 19-20 and M5 Junctions 16-17 | 2022/2023 Q2 |  | 2023/2024
FOR INFORMATION ONLY
Housing infrastructure fund schemes and third party schemes - These schemes will be delivered by local authorities and third parties with our support and are subject to future planning decisions. They are subject to different governance and funding arrangements
Delivery Plan - the date in the Highways England Delivery Plan
Start of Works forecast / actual - start of construction date as provided by external delivery organisation (third parties, local authority)
Open for Traffic forecast / actual - open for traffic date as provided by external delivery organisation (third parties, local authority)
* SOW / OFT Delivery Plan - dates updated to financial year format
External Delivery Organisation | Region | Map Ref | Scheme Name | Construction Phase
|  |  |  | Start of Works |  | Open for Traffic
|  |  |  | *Delivery Plan | Actual | *Delivery Plan | Actual
Housing infrastructure fund schemes | East | n/a | A120: Tendring/Colchester Border Garden Community | 2022/23 |  | 2024/25
| South West | n/a | M5 junction 10 and link road | 2022/23 |  | 2024/25
| South East | n/a | A249: Swale transport infrastructure | 2021/22 |  | 2024/25
| North West | n/a | M6: South Lancaster Growth Catalyst – junction 33a | 2024/25 |  | RP3
External Delivery Organisation | Region | Map Ref | Scheme Name | Construction Phase
|  |  |  | Start of Works |  | Open for Traffic
|  |  |  | Delivery Plan | Actual | Delivery Plan | Actual
Third party schemes | Midlands | n/a | A5 Towcester relief road | 2021/22 |  | RP3
| East | n/a | M11 junction 7a | 2020/21 Q2 | 2020-06-01 | 2022/23
| North West | n/a | M55 junction 2 | RP1 | 2019-09-01 | 2023/24
| North West | n/a | M62 junction 19 | 2020/21 Q3 | 2020-10-01 | 2022/23

## IP2
Statement IP2: RIS 3 Development Pipeline
No. schemes started development - total number of schemes that have started development nationally between April 2020 - March 2021
Programme level commentary - description of progress made at a national level across the RIS3 Development pipeline between April 2020 - March 2021
Region | RIS 3 Development Pipeline | Programme (National) level update
|  | No. schemes started development | Programme level commentary
North | A19 North of Newcastle Junctions | 25 | This year we have been preparing the majority of schemes to transition from S&P to MP to start development at PCF stage 1 or PCF stage 2. We have now transitioned 17 pipeline projects to MP to start the next required stage. We have also started development work on all the 7 projects which required PCF stage 0. The A21 safety package has gone through the change control process and is now being delivered in RP2 by Operations directorate. The A303 Phase 2 analytical review of the A303 corridor schemes also started this year. We expect to confirm which scheme will be progressed in the next FY.
A64 Hopgrove
M1 Leeds Eastern gateway
M1/M62 Lofthouse interchange
M6 Junctions 19 to 21a Knutsford to Croft extra capacity
M1 Junctions 35 to 39 Sheffield to Wakefield extra capacity
A1 Doncaster to Darrington
M6 junction 22
Manchester South East junction improvements
East | A47/A1101 Elm Road junction
A11 Fiveways junction
M11 junction 13 Cambridge West
A12/A14 Copdock interchange
A120 Braintree to A12
Tilbury link road
Midlands | M6 junction 15 Potteries southern access
A483 Pant-Llanymynech bypass (in cooperation with the Welsh Government)
M1 North Leicestershire extra capacity
M1 Leicester Western access
A5 Hinckley to Tamworth
South and West | Severn resilience package
A404 Bisham junction
A2 Brenley Corner
A303 Phase 2 upgrade
A3/A247 Ripley South
A21 safety package
A2 Dover Access
A27 Lewes to Polegate
A27 Chichester improvements
M27 South and Westhampton access
A38 Trerulefoot-Carkeel safety package
A404/M40 junction 4 High Wycombe

## IP3
Statement IP3: Designated funds
There are 4 designated funds outlined in Highways England's Delivery Plan 2020-2025: 1. Safety and congestion - Safety and Congestion schemes 2. User and communities - Integration; Walkers, Cyclists & Horse Riders; Roadside Facilities; Communities; Freight and Information 3. Environment and wellbeing - Biodiversity; Noise; Air quality; Flooding; Water Quality; Carbon; Cultural Heritage; Landscape and Environmental Legacy 4. Innovation and modernisation - Design, construction and maintenance; Connected and Autonomous Vehicles; Customer Mobility; Energy and Environment; Operations. Under each designated fund there are individual themes. Projects which use designated funds are aligned to a fund and an individual theme.
Key Definitions: No. planned projects completing either feasibility, detailed design or implementation 2020-2021 - The combined number of projects planned to complete either the feasibility, detailed design or implementation stage for each fund Feasibility - The number of projects that have completed the feasibility stage at the end of the year Detailed design - The number of projects that have completed the detailed design stage at the end of the year Implementation - The number of projects that have completed the implementation stage at the end of the year Comments - Justification for any deviation or any supporting commentary
Fund | Projects planned 2020-2021 | Projects delivered 2020-2021 |  |  | Total count of stages complete | Comments
| No. planned projects completing either feasibility, detailed design or implementation | Feasibility | Detailed design | Implementation
Safety and congestion fund | 20 | 2 | 7 | 22 | 31 | Safety and Congestion outperformed its baseline with 31 stage gates being passed against a target of 20. HE has delivered a larger number of stage gates than have been reported in this statement, these will require validation in 2021-22 and will be reported as part of 2021-22 performance.
Users and communities fund | 80 | 9 | 10 | 12 | 31 | Users and Communities underperformed its baseline with 31 stage gates being passed against a target of 80. HE has delivered a larger number of stage gates than have been reported in this statement, these will require validation in 2021-22 and will be reported as part of 2021-22 performance.
Environment and wellbeing fund | 110 | 27 | 18 | 24 | 69 | Environment and Wellbeing underperformed its baseline with 69 stage gates being passed against a target of 110. HE has delivered a larger number of stage gates than have been reported in this statement, these will require validation in 2021-22 and will be reported as part of 2021-22 performance.
Innovation and modernisation fund | 40 | 4 | 4 | 1 | 9 | Innovation and Modernisation underperformed its baseline with 9 stage gates being passed against a target of 40. HE has delivered a larger number of stage gates than have been reported in this statement, these will require validation in 2021-22 and will be reported as part of 2021-22 performance.

## IP4
Statement IP4: Renewal Volume Reporting
This statement details Highways England’s capital renewals delivery performance against planned volumes of activity associated with different asset types and interventions across the Strategic Road Network in 2020-21 (as set out in HE’s annual Delivery Plan).
| Asset | Description | Unit | 2020-21
Full year Actual
|  |  |  | Total | Baseline | Variance | Comments
Primary Elements | Asphalt road surface (pavement) | Total length of existing asphalt resurfaced | Lane miles | 1155.3 | 929 | 226.3 | An additional £30m from the Renewals Risk Reserve (RRR) and £25m of brought forward schemes were delivered in-year. On average the RRR delivered (6% of pavement). It's not possible to separately identify the additional scheme delivery but this included all the excess concrete pavement and would typically have delivered the same percentages as the RRR. This means that half of the over delivery was attributed to RRR and b/f and the remainder due to efficient scheme delivery.
| Concrete road surface (pavement) | Total length of existing concrete road surface reconstructed and replaced with asphalt surface | Lane miles | 37.8 | 7.5 | 30.3 | As the year progressed it became clear that the delay in major schemes works in the East would lead to road space clashes in latter part of RIS2. Therefore, the concrete programme was accelerated and the entirety of the over-delivery is due to this acceleration of the concrete programme.
| Safety barriers (steel) | Total length of steel safety barriers installed or renewed | Miles | 131.7 | 89 | 42.7 | The use of the RRR and b/f of schemes is estimated to have delivered between 6-10% more delivery and a further 10k was delivered by Designated Fund schemes. It is also estimated that 25-27.5k was also delivered alongside pavement schemes as part of efficient scheme delivery.
| Safety barriers (concrete) | Total length of concrete safety barriers installed or renewed | Miles | 8.8 | 2.5 | 6.3 | The target comprised 5 schemes only. In addition to these, a single scheme was brought into the programme in YNE to deliver 4.4k. And further 1.5k was delivered with structures schemes as part of efficient scheme delivery.
| Significant structures | Number of significant structures | Number | 44 | 44 | 0 | We achieved 44 delivery milestones against the target of 44 with 13 schemes starting design, 10 starting construction and 21 completing construction.
Secondary Elements | Road markings | Length along the centre line of the road markings, including marking on new or replacement road surfacing | Linear metres | 4829821 | 3450000 | 1379821 | Lining and kerbs are normally delivered alongside pavement schemes (see pavement comments above about additional delivery). However, these output targets are very difficult to set accurately as the precise number to be delivered cannot be known until schemes are on the ground e.g. lining length may double if planing removes both inner and outer lines. Similarly the condition on kerbing cannot be precisely known at the planning phase.
| Kerbs | Total length of kerbs laid or renewed | Linear metres | 30127 | 20500 | 9627
| Safety barriers (steel) | Total length of steel safety barriers installed or renewed | Linear metres | 211924 | 143000 | 68924 | See above
| Safety barriers (concrete) | Total length of concrete safety barriers installed or renewed | Linear metres | 14166 | 4000 | 10166 | See above
| Drainage | Total length of drainage installed or renewed | Linear metres | 158394 | 98000 | 60394 | See pavement comments above about additional delivery where up to 10% more was delivered. A further 5k was delivered through Designated Funds schemes and 28k delivered alongside pavement schemes as part of efficient scheme delivery.
| Geotechnical | Total length of embankment / cutting treated parallel to the carriageway | Linear metres | 3062 | 3000 | 62 | The target was under threat at Q3 with two schemes in SE and two schemes in East unable to be delivered. Replacement schemes were sought and SW were able to deliver geotech alongside the M5 queue and incident detection scheme.
| Traffic signs (non-electrical) | Number of permanent non-electrical traffic signs installed or replaced | Number | 1363 | 475 | 888 | 775 signs were delivered through Designated Funds schemes e.g. cycling and safety schemes where large numbers of signs are delivered as part of those schemes.
| Guardrail | Total length of new or replacement pedestrian guardrail | Linear metres | 2365 | 2300 | 65 | The guardrail target was delivered by four schemes with just 65 additional metres being delivered.
| Boundary fencing | Total length of new or replacement boundary fencing | Linear metres | 62219 | 80000 | -17781 | The target was mainly not achieved in the SW where unforeseen delays in design meant getting schemes to site at certain locations was not possible
| Lighting | Number of road lighting columns installed or replaced | Number | 1131 | 1300 | -169 | The target was mainly not achieved in YNE where the Local Authority changed requirements for a diversion route meaning a large lighting scheme was deferred into 21/22.
| Bridge joint | Number of bridge deck expansion joint installations installed or renewed | Number | 696 | 525 | 171 | More than half of joints were delivered together with pavement schemes (see comments about additional delivery) and a further 50 joints were delivered as part of emergency works.
| Bridge bearing | Number of bridge bearing units installed or renewed | Number | 130 | 110 | 20 | The original target was comprised of nine schemes. Further works were agreed on three M50 schemes to ensure delivery.
| Parapet | Total length of vehicle parapet installed or renewed | Linear metres | 7197 | 4750 | 2447 | Parapet works are mainly delivered alongside RRS works and the bulk of the additional delivery was associated with the concrete RRS as above. 450m was delivered on the Scammonden suicide prevention scheme as part of Designated Funds.
| Waterproofing | Total surface area treated for waterproofing | Square metres | 33340 | 28000 | 5340 | An additional 5k was agreed and delivered as part of the Lofthouse significant structures scheme.
| Motorway communications equipment | Number of new or replaced motorway communications equipment items | Number | 1083 | 150 | 933 | The target is difficult to set precisely as the number of components to be renewed are often not known until schemes are on the ground. There is therefore the tendency for more components to be renewed than planned.
| Technology renewals | Number of technology assets renewed or improved | Number | 420 | 325 | 95 | (see motorway comms above) The full detail of Tech Renewals are often not known until schemes are on the ground and the number of components to be replaced are often more than planned.

## IP5
Statement IP5: Maintenance Delivery Reporting
This statement details Highways England’s 2020-21 performance against a set of key maintenance activity measures. They represent a combination of planned, cyclical and reactive maintenance activities. The purpose of the statement is to provide supplementary reporting and assurance, in addition to the asset KPI’s and PI’s, that Highways England is keeping the network in good condition and meeting the requirements of the Licence to operate a safe and serviceable network.
Activity | Type | % Completed 24 Hour Priority Defects within the required timescale | % Completed within the required timescale | Comments
Defects | Paved area defects | 94.66% | 95.43% | At a national level we seen have strong performance in defect management across all asset types. Significant improvements have been made in addressing pavement defects in particular which saw an increase in performance from 90.6% and 85.6% in 2019/20 to 94.7% and 95.4% respectively in 2020/21 rectifying high priority and other defects within the required timescales.
| Road Markings and Road Studs defects | 95.1% | 93.37%
| Vehicle Restraint Systems defects | 92.7% | 93.01%
| Lighting defects | 89.82% | 86.26%
| Sign defects | 93.1% | 93.55%
| Soft estate defects (AD Areas) | 90.88% | 87.7%
| Reactive sweeping and cleaning actions (excluding graffiti) are completed (AD Areas) | 97.38% | 95.11%
| Sweeping and Cleaning - offensive graffiti | 80% | 95.64%
| Fences - defects identified related to safety | 97.71% | 95.12%
| Drainage asset defects (AD Areas) | 94% | 90.98%
| Geotechnical asset defects (AD Areas) | 100% | 100%
| Structures defects (AD Areas) | 98.31% | 96.24%
Activity | Type | % completed |  | Comments
Winter Service | The percentage of precautionary salting delivered within the precautionary salting and turnaround time as stated within the Severe Weather Plan | 100% |  | Performance maintained throughout the year at 100%
| Percentage of instances where running lanes were available in accordance with the Service Provider Severe Weather Plan in relation to snow clearance. | 100% |  | Performance maintained throughout the year at 100%
Activity | Type | % of total catchment length with a low risk status |  | Comments
Drainage | Drainage Performance Indicator | 72% |  | There has been a slight decrease in performance from Q3, due to increased rainfall resulting in higher numbers of flooding events reported. Work is being undertaken to consider actions and plans for addressing drainage performance and we expect future years investment in renewals to drive improvements to the measure.
Activity | Type | % of planned litter clearance completed |  | Comments
Litter | Percentage of planned litter clearance activities undertaken in accordance with ASC requirements or the accepted programme set out in ADAMr (AD) | 95% |  | Continued strong performance throughout the year. Slight decrease in Q4 due to adverse weather, however year end performance of 95% compares favourably to 89% achieved in 2019/20.
Activity | Type | % of cyclic works completed |  | Comments
Cyclical Maintenance (AD Areas only) | Percentage of Cyclic works that are completed within the required timescales | 77% |  | Continued improvement in performance throughout year. Improved consistency in reporting across regions accounts for the drop in performance compared to 2019/20, however positively we now have a more accurate and consistent picture across the network.
Activity | Type | % of <24hr reactive works completed |  | Comments
Reactive Maintenance (AD Areas only) | Percentage of Reactive <24hr works that are completed within the required timescales | 91% |  | Consistent and strong performance maintained throughout the year. Similarly to cyclical maintenance work to improve consistency in reporting has resulted a more accurate and consistent picture across the network.
Activity | Type | Total No of claims |  | Comments
Red Claims | Total number of claims | 1284 |  | Red claims: There was a noticeable drop in the number of red claims in 2020/21 (1751) compared to 2019/20 (1284), we believe this may be due to reduced traffic flows on the network as a result of the COVID-19 pandemic. There was a significant improvement in the number of red claims successfully settled and processed in 2020/21 with 59.5% compared to 22.5% in 2019/20. This is attributed to the improved processes and associated productivity implemented in the financial claims team.
Total No of settled claims
| Total number of settled claims | 764
Green Claims | Total number of claims | 5155 |  | Green Claims: Similarly all regions have undertaken improvement activities and the final regions to move to AD are planned in for this year. The income generated from green claims has increased substantially. 75% of green claims were successfully settled in 2020/21 compared to 18.1% in 2019/20.
Total No of settled claims
| Total number of settled claims | 3838
Activity | Type | % of programme completed |  | Comments
Planned Asset Condition Inspections | Structures | 97% |  | There has been a continued focus on the programme of inspections and ensuring inspections do not become overdue throughout 2020/21. Monthly tracking of performance at a regional and national level is now embedded across the organisation.. Of the 56 structures inspections overdue, 71% (40) have been physically undertaken and awaiting validation in IAMIS. The outstanding 29%(16) of structural inspections are all as a result of access issues and possessions.
| VRS | 84.65%
| Lighting | 116%
| Geotech | 95%
| Traffic Signs & Technology | 85%

## F1
Statement F1: Total income and expenditure
| RP1 | 2020-21 |  |  | Baseline
| Actual | Actual | Budget | Budget Difference | 2020-21 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | RIS2 Total
Resource expenditure |  |  |  |  | ** Note: HE is not funded at individual line level and these are HE working assumptions which could change annually
Operations and Maintenance (B1, B2, B3) | 2403.4 | 537.8879 | 508.0761 | -29.8118 | 508.0761 | 485.8958 | 484.7273 | 490.0502 | 493.0124 | 2461.7617
Private Finance Initiative (PFI) payments (B5) | 2135.6 | 434.6567 | 475.7062 | 41.0495 | 475.7062 | 443.9728 | 464.9519 | 473.3295 | 517.8397 | 2375.8002
Corporate Support (C1) | 799.4 | 133.0124 | 121.9342 | -11.0782 | 121.9342 | 154.747 | 162.3632 | 163.9914 | 165.1965 | 768.2323
Business Services (C2) |  | 44.9254 | 49.7257 | 4.8002 | 49.7257 | 39.7274 | 41.1022 | 43.0683 | 43.8333 | 217.4568
Protocols (D1) | 240.4 | 55.5499 | 69.0577 | 13.5078 | 69.0577 | 51.6989 | 52.089 | 52.3764 | 53.3425 | 278.5645
Total resource expenditure | 5578.8 | 1206.0419 | 1224.5 | 18.4677 | 1224.5 | 1176.0419 | 1205.2335 | 1222.8158 | 1273.2243 | 6101.8155
Capital expenditure
RIS1 Enhancements (A1) | 7059.5 | 1727.2492 | 2090.3058 | 363.0566 | 1814.8989 | 1748.4594 | 2166.4622 | 2127.6755 | 1938.7066 | 9796.2025
SR Reprofile |  | 0 | -360 | -360 | 0 | 0 | 0 | 0 | 0 | 0
RIS 2 Enhancements (A2) |  | 292.4545 | 323.88 | 31.4254 | 326.4077 | 558.2216 | 773.7267 | 1169.4593 | 1483.0071 | 4310.8224
RIS3 Development (A3) |  | 21.343 | 43.2678 | 21.9248 | 31.1817 | 45.0823 | 83.1698 | 94.4515 | 103.1662 | 357.0516
Designated Funds (A4) | X | 162.4694 | 203.475 | 41.0056 | 161.0127 | 188.5621 | 188.7459 | 204.2493 | 193.294 | 935.8639
Other capital expenditure (A5) | X | 35.6845 | 53 | 17.3155 | 0 | 0 | 0 | 0 | 0 | 0
Operations (B1, B2) | X | 187.8769 | 232.0211 | 44.1442 | 209.5 | 217.1 | 204.9 | 211.3 | 191 | 1033.8
Maintenance and Renewals (B3) | 3494 | 759.6045 | 734.4719 | -25.1326 | 706.4311 | 863.3977 | 852.7951 | 872.2954 | 971.8071 | 4266.7266
Business Costs (C1, C2) | X | 109.2252 | 148.3071 | 39.082 | 162.7 | 196.1 | 94.5 | 111.8 | 165.4 | 730.4
Total capital expenditure | 12160.3637 | 3295.9073 | 3468.7287 | 172.8214 | 3412.1322 | 3816.9231 | 4364.2997 | 4791.231 | 5046.381 | 21430.867
Total expenditure | 17739.1637 | 4501.9492 | 4693.2287 | 191.2891 | 4636.6322 | 4992.965 | 5569.5332 | 6014.0468 | 6319.6053 | 27532.7825
Resource Expenditure by Type
Income | -182.2 | -47.1519 | -29.1377 | 18.0142
Pay | 668.9 | 161.4088 | 163.4065 | 1.9977
Non-Pay | 314.45 | -41.615 | -54.7215 | -13.1065
Projects | 4777.65 | 1133.3904 | 1144.9527 | 11.5624
Total resource expenditure | 5578.8 | 1206.0323 | 1224.5 | 18.4677
Commentary:
The Opex 2020-21 outturn is an £18.5m (1%) underspend brought about by the COVID-19 impact on pay, travel, training and marketing, and on traffic volumes on Dart Charge and Private Finance Initiative contracts. The 2020-21 Capex outturn is a £172.8m underspend. £360m of funding was reprofiled to future years of the Roads Investment Strategy as part of HM Treasury’s 2020 Spending Review. The subsequent underspend was driven by Development Consent Order (DCO) delays and the impact of the late finalisation of the Roads Investment Strategy (RIS). The financial statements reconcile to the Highways England Annual Report and Accounts (AR&A), with the exception of the surplus capital funding on the M20 Moveable Barrier Solution which is shown here in the “other capital expenditure” line but is omitted from the outturn in the AR&A.

## F2
Statement F2: Regional resource income and expenditure
£m | 2020-21
| Actual | Budget | Budget Difference
Operations and Maintenance (B1, B2, B3)
Centrally managed | 136.7806 | 122.2347 | -14.546
East | 59.3883 | 64.9029 | 5.5145
Midlands | 97.4453 | 92.3254 | -5.1199
North West | 73.7404 | 63.7869 | -9.9535
South East | 75.3881 | 68.8882 | -6.4999
South West | 46.5209 | 46.5385 | 0.017603
Yorkshire & North East | 48.6242 | 49.3996 | 0.77539
Subtotal | 537.8879 | 508.0761 | -29.8118
Private Finance Initiative (PFI) payments (B5)
Centrally managed | -115.9787 | -87.6505 | 28.3282
East | 64.7886 | 69.0087 | 4.2201
Midlands | 11.1481 | 11.381 | 0.23288
North West | 0 | 0 | 0
South East | 303.2401 | 306.4879 | 3.2478
South West | 28.2323 | 28.8539 | 0.62158
Yorkshire & North East | 143.2264 | 147.6253 | 4.3989
Subtotal | 434.6567 | 475.7062 | 41.0495
Corporate Support (C1)
Centrally managed | 127.222 | 113.9311 | -13.291
East | 0 | 0 | 0
Midlands | 0.0067719 | 0 | -0.0067719
North West | 0.032331 | -8.8e-07 | -0.032332
South East | 5.7216 | 8.0032 | 2.2815
South West | 0.029122 | 0 | -0.029122
Yorkshire & North East | 0 | 0 | 0
Subtotal | 133.0119 | 121.9342 | -11.0777
Business Services (C2)
Centrally managed | 44.8608 | 49.7257 | 4.8649
East | 0 | 0 | 0
Midlands | 0.0006033 | 0 | -0.0006033
North West | 0.0031751 | 0 | -0.0031751
South East | 0 | 0 | 0
South West | 0.011874 | 0 | -0.011874
Yorkshire & North East | 0.049016 | 0 | -0.049016
Subtotal | 44.9254 | 49.7257 | 4.8002
Protocols (D1)
Centrally managed | 32.0086 | 44.8699 | 12.8612
East | 0 | 0 | 0
Midlands | 0.05478 | 0.054783 | 3e-06
North West | 0 | 0 | 0
South East | 0 | 0 | 0
South West | 10.5042 | 10.9773 | 0.4731
Yorkshire & North East | 12.9823 | 13.1557 | 0.17347
Subtotal | 55.5499 | 69.0577 | 13.5078
Total | 1206.0318 | 1224.5 | 18.4682
Commentary:
The Opex 2020-21 outturn is an £18.5m (1%) underspend brought about by the COVID-19 impact on pay, travel, training and marketing, and on traffic volumes on Dart Charge and Private Finance Initiative contracts.

## F2.1
Statement F2.1: Resource income and projects expenditure
£m |  | 2020-21
|  | Actual | Budget | Budget Difference
Operations and Maintenance (B1, B2, B3)
Non-projects | Pay | 85.5522 | 89.3041 | 3.7518
| Non-pay | 12.0019 | 11.4651 | -0.53681
| Income | -38.8029 | -23.6362 | 15.1667
| Non-projects Subtotal | 76.7614 | 77.133 | 0.37154
Projects - Maintenance and Renewals | Routine Maintenance | 273.2317 | 240.8426 | -32.3891
| Winter Maintenance | 3.6529 | 2.9086 | -0.74434
| Technology - Maintenance | 34.3629 | 33.3474 | -1.0156
| Renewal of Roads | 1.4865 | 0.84659 | -0.63987
| Renewal of Structures | 9.1145 | 11.1407 | 2.0262
| Other Maintenance | 2.7563 | 2.2 | -0.5563
Projects - General Operations | S274/S278 Works | 15.5778 | 3.1828 | -12.395
| Technology | 37.1549 | 18.9135 | -18.2414
| Other | 68.64 | 86.9935 | 18.3536
Projects - Customer Operations | Traffic Management | 31.9877 | 28.8009 | -3.1869
| Traffic Officer Service | 1.1714 | 1.7666 | 0.59515
| Projects Subtotal | 479.1367 | 430.9432 | -48.1935
| Total | 537.8879 | 508.0761 | -29.8118
PFI (Private Finance Initiative)
Non-projects | Pay | 0 | 0 | 0
| Non-pay | -81.2072 | -86.7907 | -5.5835
| Income | 0 | 0 | 0
| Non-projects Subtotal | -81.2072 | -86.7907 | -5.5835
Projects | A1(M) Darrington to Dishforth | 62.0058 | 64.6338 | 2.628
| A19 Dishforth to Tyne Tunnel | 71.0528 | 70.632 | -0.42079
| A249 Iwade to Queenborough | 13.9925 | 13.8028 | -0.1897
| A30/A35 Exeter to Bere Regis | 9.6133 | 9.6324 | 0.019102
| A419/A417 Swindon to Gloucester | 18.619 | 19.2215 | 0.60248
| A50/A564 Stoke - Derby link | 11.1481 | 11.381 | 0.23288
| A69 Carlisle to Newcastle | 11.5248 | 12.1765 | 0.65174
| M1-A1 Yorkshire link | 22.8388 | 27.0141 | 4.1753
| M25 London Orbital Motorway contract | 289.2475 | 292.6851 | 3.4375
| M40 Junctions 1-15 | 40.5928 | 42.1776 | 1.5848
| Other | -34.7716 | -0.85982 | 33.9117
| Projects Subtotal | 515.8639 | 562.4969 | 46.633
| Total | 434.6567 | 475.7062 | 41.0495
Corporate Support (C1)
Non-projects | Pay | 46.6802 | 44.0381 | -2.642
| Non-pay | 36.8314 | 27.1726 | -9.6588
| Income | -7.4208 | -5.2016 | 2.2192
| Non-projects Subtotal | 76.0907 | 66.0092 | -10.0816
Projects | Lands | 52.3116 | 55.9251 | 3.6135
| Other | 4.61 | 0 | -4.61
| Projects Subtotal | 56.9217 | 55.9251 | -0.99658
| Total | 133.0124 | 121.9342 | -11.0782
Business Services (C2)
Non-projects | Pay | 22.7021 | 21.4438 | -1.2582
| Non-pay | -9.4111 | -7.5395 | 1.8716
| Income | -0.64485 | 0 | 0.64485
| Non-projects Subtotal | 12.6461 | 13.9044 | 1.2582
Projects | Research and Development | 8.8942 | 8.5 | -0.39417
| Other | 23.3851 | 27.3213 | 3.9362
| Projects Subtotal | 32.2793 | 35.8213 | 3.542
| Total | 44.9254 | 49.7257 | 4.8002
Protocols (D1)
Non-projects | Pay | 6.4744 | 8.6204 | 2.146
| Non-pay | 0.17 | 0.97102 | 0.80102
| Income | -0.28338 | -0.3 | -0.016618
| Non-projects Subtotal | 6.361 | 9.2915 | 2.9304
Projects |  | 49.1889 | 59.7662 | 10.5774
| Projects Subtotal | 49.1889 | 59.7662 | 10.5774
| Total | 55.5499 | 69.0577 | 13.5078
| Total resource expenditure | 1206.0323 | 1224.5 | 18.4677

## F2.2
Statement F2.2: Analysis of protocols expenditure
| 2020-21 |  |  | 2015-16 | 2016/17 | 2017-18 | 2018-19 | 2019-20 | RIS 1 Total
| Actual | Budget | Budget Difference | Baseline v1.1 | Baseline v1.1 | Baseline v1.1 | Baseline v1.1 | Baseline v1.1 | Baseline v1.1
Abnormal Loads | 0.83592 | 1.6808 | 0.84493 | 1.1281 | 1.157 | 1.1859 | 1.1859 | 1.2148 | 5.8717
Dart Charge | 25.1181 | 36.2016 | 11.0835 | 26.1965 | 26.8682 | 27.5399 | 27.5399 | 28.2116 | 136.356
M6 Toll | 0.05478 | 0.054783 | 3e-06 | 0.041548 | 0.042614 | 0.043679 | 0.043679 | 0.044744 | 0.21626
Historical Railways Estate | 13.0051 | 13.2405 | 0.23541 | 7.1715 | 7.3554 | 7.5393 | 7.5393 | 7.7232 | 37.3287
National Salt Reserve | 0.4643 | 1.3008 | 0.83649 | 0.90342 | 0.92659 | 0.94975 | 0.94975 | 0.97292 | 4.7024
Severn Crossings up to the end of the concession | 13.9717 | 14.4792 | 0.50748 | 1.9281 | 1.9776 | 2.027 | 2.027 | 2.0764 | 10.0362
Technical Regulations | 2.1 | 2.1 | 2.92e-05 | 1.6308 | 1.6726 | 1.7145 | 1.7145 | 1.7563 | 8.4887
Total Protocols Expenditure | 55.5499 | 69.0577 | 13.5078 | 39 | 40 | 41 | 41 | 42 | 203

## F2.3
Statement F2.3: Analysis of FTE expenditure
| 2020-21 |  |  | 2015-16 | 2016/17 | 2017-18 | 2018-19 | 2019-20 | RIS 1 Total
| Actual | Budget | Budget Difference | Baseline v1.1 | Baseline v1.1 | Baseline v1.1 | Baseline v1.1 | Baseline v1.1 | Baseline v1.1
Centrally Managed | 0 | 0 | 0 | 1.1281 | 1.157 | 1.1859 | 1.1859 | 1.2148 | 5.8717
Commercial and Procurement | 439.0967 | 481.7918 | 42.6951 | 26.1965 | 26.8682 | 27.5399 | 27.5399 | 28.2116 | 136.356
Communications Directorate | 133.1892 | 134.172 | 0.9828 | 0.041548 | 0.042614 | 0.043679 | 0.043679 | 0.044744 | 0.21626
Finance and Business Services | 374.3822 | 366.929 | -7.4532 | 7.1715 | 7.3554 | 7.5393 | 7.5393 | 7.7232 | 37.3287
Human Resources | 109.2775 | 97.6543 | -11.6232 | 0.90342 | 0.92659 | 0.94975 | 0.94975 | 0.97292 | 4.7024
Major Projects | 784.4504 | 789.2184 | 4.768 | 1.9281 | 1.9776 | 2.027 | 2.027 | 2.0764 | 10.0362
Lower Thames Crossing | 31.7108 | 4 | -27.7108
Operations | 3185.6222 | 3411.091 | 225.4688 | 1.6308 | 1.6726 | 1.7145 | 1.7145 | 1.7563 | 8.4887
Information Technology Directorate | 229.1728 | 254.7637 | 25.5909
Safety, Engineering and Standards | 410.0511 | 417.3618 | 7.3107
Strategy and Planning | 169.5162 | 167.0721 | -2.4441
General Counsel | 43.2458 | 46.36 | 3.1142
FTE Total | 5909.7149 | 6170.414 | 260.6991 | 39 | 40 | 41 | 41 | 42 | 203
2020-21
| Actual | Budget | Budget Difference
Centrally managed | 2599.6231 | 2574.0568 | -25.5663
East | 632.6459 | 785.4261 | 152.7802
Midlands | 605.2345 | 589.2459 | -15.9886
North West | 645.2761 | 618.4705 | -26.8056
South East | 526.3489 | 709.753 | 183.4041
South West | 440.0812 | 440.874 | 0.7928
Yorkshire & North East | 460.5052 | 452.5877 | -7.9175
FTE Total | 5909.7149 | 6170.414 | 260.6991

## F3
Statement F3: Capital expenditure
£m | Activity | 2020-21 |  |  | Baseline
|  | Actual | Budget | Budget Difference | 2020-21 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | RIS2 Total
Maintenance and Renewals
| Renewal of Roads | 521.4786 | 502.7151 | -18.7636 | x | x | x | x | x | x
| Renewal of Structures | 176.1501 | 167.0968 | -9.0533
| Renewal of Technology | 35.7299 | 33.5904 | -2.1395
| Winter Maintenance - Assets | 26.1793 | 31.0698 | 4.8905
| Total Maintenance and Renewals | 759.5378 | 734.4719 | -25.0659 | 706.4311 | 863.3977 | 852.7951 | 872.2954 | 971.8071 | 4266.7266
RIS1 Enhancements
| Regional Investment Programme | 654.5708 | 694.6418 | 40.071 | 687.8 | 982.1 | 1178.3 | 1180.8 | 1192.9 | 5221.9
| Smart Motorways Programme | 876.8929 | 881.8071 | 4.9142 | 867 | 406.9 | 303.6 | 213.7 | 164.2 | 1955.4
| Complex Infrastructure Programme | 131.576 | 180.5627 | 48.9867 | 164.5 | 206.7 | 596.7 | 572.1 | 399.4 | 1939.4
| Other RIS1 expenditure including Portfolio Risk/Contingency and Surplus Funding | 64.2094 | 333.2941 | 269.0847 | 95.5989 | 152.7594 | 87.8622 | 161.0755 | 182.2066 | 679.5025
| Total RIS1 Enhancements | 1727.2492 | 2090.3058 | 363.0566 | 1814.8989 | 1748.4594 | 2166.4622 | 2127.6755 | 1938.7066 | 9796.2025
RIS2 Enhancements
| Regional Investment Programme | 41.9887 | 40.2345 | -1.7542 | 43.2 | 53.5 | 78 | 249.1 | 315.3 | 739.1
| Smart Motorways Programme | 14.3747 | 0 | -14.3747 | 27.6 | 190.9 | 137.1 | 102.4 | 113 | 571
| Complex Infrastructure Programme | 0.020784 | 0 | -0.020784 | 0 | 1 | 2 | 3 | 4 | 10
| Lower Thames Crossing | 234.9778 | 245.1954 | 10.2177 | 254 | 282.4 | 475.8 | 741.7 | 935.8 | 2689.7
| Other RIS2 expenditure including Portfolio Risk/Contingency | 1.0925 | 38.45 | 37.3575 | 1.6077 | 30.4216 | 80.8267 | 73.2593 | 114.9071 | 301.0224
| Total RIS2 Enhancements | 292.4545 | 323.88 | 31.4254 | 326.4077 | 558.2216 | 773.7267 | 1169.4593 | 1483.0071 | 4310.8224
RIS3 Development
|  | 21.343 | 43.2678 | 21.9248 | 31.1817 | 45.0823 | 83.1698 | 94.4515 | 103.1662 | 357.0516
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0
| Total RIS3 Development | 21.343 | 43.2678 | 21.9248 | 31.1817 | 45.0823 | 83.1698 | 94.4515 | 103.1662 | 357.0516
Designated Funds
| Environment and Wellbeing | 58.1661 | 93.475 | 35.3089 | 43.2367 | 84.6721 | 88.7939 | 99.8473 | 94.314 | 410.8639
| Innovation and Modernisation | 39.1066 | 40 | 0.89337 | 40 | 40 | 42 | 47 | 47 | 216
| Safety and Congestion Fund | 33.6175 | 30 | -3.6175 | 37.776 | 31.89 | 25.952 | 24.402 | 19.98 | 140
| Users and Communities | 31.5792 | 40 | 8.4208 | 40 | 32 | 32 | 33 | 32 | 169
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Designated Funds | 162.4694 | 203.475 | 41.0056 | 161.0127 | 188.5621 | 188.7459 | 204.2493 | 193.294 | 935.8639
Operations, Business Costs and Other Capital
| Operations | 187.8769 | 232.0211 | 44.1442 | 209.5 | 217.1 | 204.9 | 211.3 | 191 | 1033.8
| Business Costs | 109.2252 | 148.3071 | 39.082 | 162.7 | 196.1 | 94.5 | 111.8 | 165.4 | 730.5
| Other Capital | 35.6845 | 53 | 17.3155 | 0 | 0 | 0 | 0 | 0 | 0
| Total Operations, Business Costs and Other Capital | 332.7867 | 433.3283 | 100.5416 | 372.2 | 413.2 | 299.4 | 323.1 | 356.4 | 1764.3
Commentary:
The 2020-21 Capex outturn is a £172.8m underspend. HM Treasury’s 2020 Spending Review facilitated a RIS2 funding reprofile. This included taking £360m out of this year and providing it in later years where it is required. The subsequent underspend arose due to the impact of Development Consent Order (DCO) delays and the late finalising of the RIS impacting on the extent to which Designated Funds and RIS3 programmes could be mobilised in-year. Separately there is £17m of surplus funding from the Department for the M20 Moveable Barrier Solution.

## F3.1
Statement F3.1 : Enhancement expenditure
£m | Scheme name | 2020-21
|  | Actual | Budget | Budget Difference
RIS1 Enhancements
| A1 Birtley to Coal House | 13.1193 | 12.9717 | -0.14762
| A1 Morpeth to Ellingham and A1 North of Ellingham | 20.0692 | 18.9587 | -1.1105
| A1 Scotswood to North Brunton | 33.2788 | 29.6542 | -3.6246
| A12 Chelmsford to A120 | 32.31 | 25.7716 | -6.5384
| A14 Cambridge to Huntingdon | 77.3679 | 71.7893 | -5.5786
| A19 Down Hill Lane | 14.9881 | 18.5382 | 3.5501
| A19 Norton to Wynyard | 46.9885 | 44.7227 | -2.2658
| A19 Testos | 46.3598 | 49.999 | 3.6391
| A2 Bean and Ebbsfleet | 24.3915 | 20.7731 | -3.6184
| A27 Arundel Bypass | 14.0271 | 13.6 | -0.42707
| A27 East of Lewes Package | 14.7555 | 23.9334 | 9.1779
| A27 Worthing and Lancing improvements | 0.2584 | 0 | -0.2584
| A30 Chiverton to Carland Cross | 43.2388 | 27.5171 | -15.7218
| A303 Amesbury to Berwick Down | 26.9184 | 63.115 | 36.1965
| A303 Sparkford to Ilchester | 8.624 | 10.2154 | 1.5914
| A31 Ringwood | 2.741 | 2.1052 | -0.63584
| A34 Newbury to Oxford Enhancements | 0.86328 | 4.474 | 3.6107
| A358 Taunton to Southfields | 7.7588 | 19.9399 | 12.1812
| A38 Derby Junctions | 11.2493 | 14.06 | 2.8107
| A428 Black Cat to Caxton Gibbet | 24.9033 | 41.0785 | 16.1752
| A45/A6 Chowns Mill Junction | 13.6836 | 10.68 | -3.0036
| A46 Coventry Junctions | 16.0239 | 17.8711 | 1.8472
| A47 Blofield to North Burlingham | 4.0033 | 5.0186 | 1.0153
| A47 Guyhirn Junction | 4.38 | 4.3203 | -0.059713
| A47 North Tuddenham to Easton | 7.7071 | 11.1263 | 3.4192
| A47 Thickthorn Junction | 3.2825 | 3.5531 | 0.27051
| A47 Wansford to Sutton | 2.9343 | 3.5892 | 0.65494
| A5 Dodwells to Longshoot | -0.012546 | 0.25701 | 0.26955
| A500 Etruria | 1.0972 | 3.4032 | 2.306
| A5036 Princess Way | 1.3444 | 2.2035 | 0.85907
| A52 Nottingham Junctions | 1.9943 | 4 | 2.0057
| A585 Windy Harbour to Skippool | 23.564 | 29.8506 | 6.2866
| A61 Westwood Roundabout | 13.6425 | 14.5464 | 0.90387
| A63 Castle Street | 48.5344 | 44.3026 | -4.2317
| M1 Junctions 13-19 | 165.8621 | 135.0646 | -30.7975
| M2 Junction 5 | 4.0936 | 19.8238 | 15.7302
| M25 Junction 10 | 13.4572 | 17.6651 | 4.2079
| M25 Junction 25 | 3.8785 | 6.9315 | 3.053
| M25 Junction 28 | 6.5705 | 4.0856 | -2.4849
| M25 Junctions 10-16 | 5.1074 | 5.3425 | 0.23505
| M27 Junctions 4-11 | 125.7276 | 117.8801 | -7.8476
| M27 Southampton Junction 8 | 1.7206 | 8.6612 | 6.9405
| M3 Junction 9 | 5.0213 | 2.698 | -2.3233
| M3 Junctions 9-14 | 9.8587 | 20.8238 | 10.9651
| M4 Junctions 3-12 | 329.8769 | 311.2076 | -18.6693
| M40/M42 Interchange | 4.7979 | 5.3072 | 0.50931
| M42 Junction 6 | 23.7923 | 36.5043 | 12.712
| M49 Avonmouth Junction | 4.7979 | 5.3072 | 0.50931
| M54-M6 Link Road | 7.8346 | 9.2179 | 1.3833
| M56 Junctions 6-8 | 18.1315 | 25.2186 | 7.087
| M6 Junction 10 | 14.7413 | 12.5672 | -2.1741
| M6 Junction 19 | 26.0602 | 28.5275 | 2.4673
| M6 Junctions 13-15 | 97.7331 | 102.9382 | 5.2051
| M6 Junctions 21a-26 | 10.815 | 14.1344 | 3.3194
| M62 Junctions 20-25 | 8.1442 | 14.9105 | 6.7663
| M621 Junctions 1-7 | 2.9102 | 7.8612 | 4.951
| Mottram Moor Link Road & A57 Link Road | 5.7936 | 4.6715 | -1.1221
| M62 Junctions 25-30 | 1.3918 | 2.7975 | 1.4057
| A47 Great Yarmouth Junctions | 0.092442 | 0 | -0.092442
| Other RIS1 expenditure | 222.6485 | 502.2201 | 279.5716
| Total RIS1 Enhancements | 1727.2492 | 2090.3058 | 363.0566
RIS2 Enhancements
| A46 Newark Bypass | 1.1863 | 1.2264 | 0.040164
| A417 Air Balloon | 18.843 | 18.6635 | -0.17956
| M60/M62/M66 Simister Island Interchange | 0.93448 | 1.0468 | 0.11231
| Lower Thames Crossing and Lower Thames Crossing Top Up | 234.9985 | 245.1954 | 10.1969
| A66 Northern Trans-Pennine | 13.7437 | 13.4901 | -0.25364
| M5 Junctions 16-17 | 0.15683 | 0 | -0.15683
| M42 Junctions 4-7 | 0.21848 | 0 | -0.21848
| M6 Junctions 4-5 | 0.37552 | 0 | -0.37552
| M6 Junctions 5-8 | 0.26256 | 0 | -0.26256
| M6 Junctions 8-10a | 0.17451 | 0 | -0.17451
| Other RIS2 expenditure | 21.5606 | 44.2577 | 22.6972
| Total RIS2 Enhancements | 292.4545 | 323.88 | 31.4254

## F3.2
Statement F3.2: Regional capital income and expenditure
£m | 2020-21
| Actual | Budget | Budget Difference
Maintenance & Renewals
Centrally managed | 18.5001 | 30.8352 | 12.3351
East | 128.477 | 128.7481 | 0.27117
Midlands | 164.6969 | 154.3685 | -10.3284
North West | 130.735 | 123.5174 | -7.2176
South East | 112.9369 | 101.2477 | -11.6892
South West | 95.1746 | 90.4264 | -4.7481
Yorkshire & North East | 109.0174 | 105.3286 | -3.6888
Subtotal | 759.5378 | 734.4719 | -25.0659
RIS1 Enhancements
Centrally managed | 5.3216 | 266.889 | 261.5675
East | 178.6545 | 188.4531 | 9.7985
Midlands | 375.5235 | 369.3136 | -6.21
North West | 157.1519 | 181.6197 | 24.4677
South East | 648.5777 | 663.2718 | 14.6941
South West | 101.9554 | 140.8064 | 38.851
Yorkshire & North East | 260.0645 | 279.9523 | 19.8878
Subtotal | 1727.2492 | 2090.3058 | 363.0566
RIS2 Enhancements
Centrally managed | 13.8171 | 38.45 | 24.6329
East | 6.5406 | 5.6071 | -0.93345
Midlands | 2.4708 | 1.2264 | -1.2443
North West | 14.8894 | 14.7375 | -0.15195
South East | 235.3596 | 245.1954 | 9.8358
South West | 18.9999 | 18.6635 | -0.33639
Yorkshire & North East | 0.37717 | 0 | -0.37717
Subtotal | 292.4545 | 323.88 | 31.4254
RIS3 Development
Centrally managed | 6.0356 | 24.7409 | 18.7053
East | 0 | 0 | 0
Midlands | 0.81115 | 0.906 | 0.094849
North West | 5.015 | 5.4 | 0.38503
South East | 5.8852 | 8.3937 | 2.5085
South West | 1.1786 | 1.4287 | 0.25008
Yorkshire & North East | 2.4174 | 2.3985 | -0.018948
Subtotal | 21.343 | 43.2678 | 21.9248
Designated Funds
Centrally managed | 58.5096 | 135.6038 | 77.0941
East | 9.8029 | 12.1409 | 2.338
Midlands | 10.0047 | 8.3049 | -1.6998
North West | 14.9873 | 7.0017 | -7.9856
South East | 27.0547 | 14.6748 | -12.3799
South West | 22.5279 | 10.2426 | -12.2853
Yorkshire & North East | 19.5759 | 15.5063 | -4.0696
Subtotal | 162.463 | 203.475 | 41.012
Operations, Business Costs, and Other Capital
Centrally managed | 260.5898 | 334.3031 | 73.7133
East | 4.359 | 9.1525 | 4.7935
Midlands | 7.4001 | 7.025 | -0.37508
North West | 7.0003 | 8.9127 | 1.9124
South East | 44.6559 | 63.6792 | 19.0233
South West | 3.5373 | 3.5872 | 0.04993
Yorkshire & North East | 5.2442 | 6.6684 | 1.4242
Subtotal | 332.7867 | 433.3283 | 100.5416
Total | 3295.8342 | 3828.7287 | 532.8945
Commentary:
Capital expenditure by geographic region is available and reported to the Department annually.